Workpackage 8: Dissemination and feedback

Objectives

To have feedback on the provisional results of the project and to disseminate the final results of the project to three different target groups:

- stakeholders in the social and institutional environment of food chains (e.g. politicians, consumer organisations, environmental groups, etc.)

- actors in the food chain (e.g. farmers, retailers, processing industry, etc.)

- the scientific community (agricultural sciences, environmental sciences, consumer studies, economy, sociology, rural studies, etc.).

Methodology and study materials

- SUS-CHAIN website: As soon as the project starts P1 will develop a SUS-CHAIN website, which will be launched at the start of this workpackage. P1 will maintain and update the website throughout the project. All synthesis reports, executive summaries of national reports and reports of the national seminars will be placed on the website. The website will also entail descriptions of the participants and subcontractors, brief CV's of the scientific teams and links to websites of relevant stakeholders' organisations. The website is a means to disseminate results to different target groups.

- Dissemination plan : At the start of the workpackage P7 (in collaboration with P1) will write a dissemination plan, outlining in detail the practical implications (e.g. target groups, timetable for deliverables, methodology for the national seminars, etc.) of the dissemination strategy as described in section 5 of the technical annex.

- National seminar 1: In month 9 the subcontractors will organise the first national seminar to disseminate the provisional results of WP1, 2 & 3 to the target groups and to get feedback on the provisional sets of performance indicators (WP1) and on the state of the art concerning the dynamics of food supply chains (WP2) and consumers' attitudes (WP3). The seminar is also intended to get suggestions from the target groups for the case studies (WP5).

- National seminar 2: In month 20 the subcontractors will organise the second national seminar to disseminate the provisional results of the case studies and get feedback on these provisional results. In addition the second seminar is intended to collectively assess the opportunities and constraints for improving the performance of food supply chains.

- National seminar 3: In month 31 the subcontractors will organise the third national seminar to disseminate the provisional practical and policy recommendations and to fine-tune the recommendations on the basis of the feedback given by the target groups.

- International conference: In month 33 P5 will, in collaboration with P1 organise an international conference especially oriented at Commission representatives and policy makers / stakeholders' organisations from the participating countries. At the conference the major policy recommendations and the protocol to enhance the collective performance of sustainable food chains will be presented.

- Scientific book: P1 will, together with P5 and P6, edit a scientific book, which will discuss the potential role of new food supply chains in sustainable rural development. All contractors and subcontractors will contribute to this book by writing and submitting empirical, methodological and/or theoretical papers.

- Final report: P1 will write a final report according to the Commission guidelines.

Deliverables

D5.	Dissemination plan (R – CO)

D6.	SUS-CHAIN website (O – PU) ( input for all workpackages

D7.	National seminar 1 (C – RE/PU) ( input for WP1, WP2, WP3, WP4

D15.	National seminar 2 (C – RE/PU) ( input for WP1, WP5, WP6

D19.	National seminar 3 (C – RE/PU) ( input for WP7

D22.	International conference (C – PU) ( input for WP7

D24.	Scientific book (R – PU)

D25.	SUS-CHAIN final report (R – PU)

Milestones

M6	The role of food supply chains in sustainable rural development. Empirical, methodological and theoretical results, summarising all findings of the project. Final result of workpackage 8, builds on all previous workpackages.